## Release_Plan
ID | Task Mode | GO LIVE | Task Name | Details Task | Validation | CHG No. | % Complete | Duration | Start | Finish | Resource Names | Comments / Notes
0 | prerequisite | y | 1. Asset team to share on-premises GPG encryption key (secring.gpg). 2. Asset team to share on-premises GPG encryption passphrase. (The above two points only applicable for on-premises files migration, for BAU it's not needed). 3. Make sure that the below file is configured correctly with require AWS production details. "https://github.aus.thenational.com/wis-ansible/wis-archive-env-config-prod/blob/master/group_vars/all.yml" | [7 empty] | George Pavone
1 | Manual | y | Create S3 bucket "nab-wealthintprod-prod-wis-artifact" using AWS console. | 1. Login into prod AWS console using browser. 2. Navigate to the S3 page and create the S3 bucket name "nab-wealthintprod-prod-wis-artifact" 3. Create the "private" folder at root, under private folder copy "secring.gpg" file (The on-premises GPG encryption key). | 1. The S3 "nab-wealthintprod-prod-wis-artifact" must be created. 2. On-premises GPG encryption key file must be present under "Amazon S3/nab-wealthintprod-prod-wis-artifact/private/secring.gpg" |  |  | 10 minutes? | 2021-04-30 13:50 | 2021-04-30 14:00 | Venkata Kishore K Kantipudi
2 | Auto Scheduled | y | Create the wis-archive folder at Jenkins dashboard and configure "deploy-archival-lambda" pipelines. | 1.Navigate to the wis-archive folder from Jenkins dashboard, click on the "New Item" from left hand side menu, enter deploy-archival-lambda in "Enter an item name" text box and select "Pipeline" form the list. 2.Under Pipeline tab, under "Definition" section select "Pipeline script from SCM", under "SCM" select "Git", Under "Repositories, Repository name" enter git@github.aus.thenational.com:wis-ansible/wis-archive-lambda.git, in "Credential" select none, under "Branches to build, Branch Specifier (blank for 'any')" enter */master, for "Repository browser" select "Auto", under "Script Path" enter Jenkinsfile and select "Lightweight checkout" check box. 3. Keep other Jenkins settings as default and click on "Save" button. | Deploy Archival Lambda Jenkins pipeline is configured for prod deployment. |  | 0% | 10 minutes? | 2021-04-30 14:00 | 2021-04-30 14:10 | Venkata Kishore K Kantipudi
3 | Auto Scheduled | y | Configure "deploy-retrieval-lambda" pipelines under wis-archive folder in prod Jenkins. | 1.Navigate to the wis-archive folder from Jenkins dashboard, click on the "New Item" from left hand side menu, enter deploy-retrieval-lambda in "Enter an item name" text box and select "Pipeline" form the list. 2.Under Pipeline tab, under "Definition" section select "Pipeline script from SCM", under "SCM" select Git, Under "Repositories, Repository name" enter git@github.aus.thenational.com:wis-ansible/wis-retrieve-lambda.git, in "Credential" select none, under "Branches to build, Branch Specifier (blank for 'any')" enter */master, for "Repository browser" select "Auto", under "Script Path" enter Jenkinsfile and select "Lightweight checkout" check box. 4. Keep other Jenkins settings as default and click on "Save" button. | Deploy Retrieval Lambda Jenkins pipeline is configured successfully for prod deployment. |  | 0% | 10 minutes? | 2021-04-30 14:10 | 2021-04-30 14:20 | Venkata Kishore K Kantipudi
4 | Auto Scheduled | y | Configure "create-wis-archive-stack" pipelines under wis-archive folder in prod Jenkins. | 1.Navigate to the wis-archive folder from Jenkins dashboard, click on the "New Item" from left hand side menu, enter create-wis-archive-stack in "Enter an item name" text box and select "Freestyle project" form the list. 2.Under "Source Code Management" tab, select "Git",under "Repositories, Repository URL" enter "git@github.aus.thenational.com:wis-ansible/wis-archive-playbook.git" in "Credential" select none, under "Branches to build, Branch Specifier (blank for 'any')" enter */master, for "Repository browser" select "Auto". 3.Under "Build Environment" tab, under "Build", "Execute Shell, Command" section enter below two line in separate line sudo /bin/su -c "cd /var/lib/Jenkins/workspace/${JOB_NAME}; make execute ENV_NAME=prod ENV_GIT_TAG=master DEBUG=true" - root 4. Keep other Jenkins settings as default and click on "Save" button. | Create wis-archival stack Jenkins pipeline is configured for prod deployment. |  | 0% | 10 minutes? | 2021-04-30 14:20 | 2021-04-30 14:30 | Venkata Kishore K Kantipudi
3 | Auto Scheduled | y | Build "deploy-archival-lambda" Jenkins pipeline. | It will clone the Archival Lambda source code from GitHub repository "git@github.aus.thenational.com:wis-ansible/wis-archive-lambda.git", build it using maven and Java SDK and save the Jar file into AWS S3 "nab-wealthintprod-prod-wis-artifact" bucket. | 1. Success: "archive-lambda.jar" will be located in AWS S3 "nab-wealthintprod-prod-wis-artifact" bucket under lambda folder. 2. Failed: Need to check Jenkins pipeline job "console output" for error details. |  | 0% | 30 minutes? | 2021-04-30 14:30 | 2021-04-30 15:00 | Venkata Kishore K Kantipudi
4 | Auto Scheduled | y | Build "deploy-retrieval-lambda" Jenkins pipeline. | It will clone the Retrieval Lambda source code from GitHub repository "git@github.aus.thenational.com:wis-ansible/wis-retrieve-lambda.git", build it using maven and Java SDK and save the Jar file into AWS S3 "nab-wealthintprod-prod-wis-artifact" bucket. | 1. Success: "retrieval-lambda.jar" will be located in AWS S3 "nab-wealthintprod-prod-wis-artifact" bucket under lambda folder. 2. Failed: Need to check Jenkins pipeline job "console output" for error details. |  | 0% | 30 minutes? | 2021-04-30 15:00 | 2021-04-30 15:30 | Venkata Kishore K Kantipudi
5 | Auto Scheduled | y | 1.Template to lunch AWS resources. 2. Build "create-wis-archive-stack" Jenkins pipeline. | It will clone the Archival Playbook ansible/ AWS CloudFormation script code from GitHub repository "git@github.aus.thenational.com:wis-ansible/wis-archive-playbook.git", It will also clone the AWS environment specific configuration from GitHub repository "git@github.aus.thenational.com:wis-ansible/wis-archive-env-config-prod.git". | Failed: Need to check Jenkins pipeline job "console output" for error details. Success: 1. It will create the "tibco-prod-app-wis-archive-CloudFormation" stack in AWS prod account under CloudFormation AWS service. 2. Also It will launch and configured below AWS resources a. S3 buckets i. nab-wealthintprod-prod-wis-archival-source ii. nab-wealthintprod-prod-wis-archival iii. nab-wealthintprod-prod-wis-retrieval iv. nab-wealthintprod-prod-wis-temp-retrieval b. Lambda i. wis-archive-prod-ArchivalLambda ii. wis-archive-prod-RetrievalLambda c. Lambda Role i. wis-archive-prod-app-S3FullAccess-LambdaRole d. Lambda Security Group i. wis-archive-prod-app-lambda e.Lambda Permission for i. Temp Retrieval Bucket. ii. Archival Bucket f. EFS File System g. EFS mount target availability zone i. Availability zone - A ii. Availability zone - B iii. Availability zone - C h. EFS access point i. KMS Key i. Lambda ii. S3 bucket i. KMS Key Alias i. alias/nab-wealthintprod-lambda-prod-wis-archive-kmskey ii. alias/nab-wealthintprod-s3-prod-wis-archive-kmskey |  | 0% | 1.5 hours? | 2021-04-30 15:30 | 2021-04-30 17:00 | Venkata Kishore K Kantipudi
6 | Auto Scheduled | y | Verify AWS resources and configured. | 1. Check Environment variables Lambda. a. Archival lambda: i. batchSize => 1000 (Might be different based on lambda performance) ii. bucketName => nab-wealthintprod-prod-wis-archival iii. bufferSize => 1024 iv. http_proxy => http://forwardproxy:3128 v. https_proxy => http://forwardproxy:3128 vi. keyArn => Lambda KMS Key ARN vii. no_proxy =>localhost,127.0.0.1,169.254.169.254,s3.ap-southeast-2.amazonaws.com viii. passphrase => GPG encryption on-premises Passphrase. xi. privateKeyBucket => nab-wealthintprod-prod-wis-artifact (This applicable only onprem migration) x. sourceBucketName => nab-wealthintprod-prod-wis-archival-source (This applicable only onprem migration). xi. region => ap-southeast-2 xii. sourcePath => /mnt/efs b. Retrieval lambda: i. destinationBucket => nab-wealthintprod-prod-wis-retrieval ii. http_proxy => http://forwardproxy:3128 iii. https_proxy => http://forwardproxy:3128 vi. keyArn => Lambda KMS Key ARN v. no_proxy =>localhost,127.0.0.1,169.254.169.254,s3.ap-southeast-2.amazonaws.com vi. region => ap-southeast-2 vii. temporaryBucket => nab-wealthintprod-prod-wis-temp-retrieval viii. temporaryDirectory => /mnt/efs/processing 2. Network configuration for Archival and Retrieval lambda i. VPC - wealthint-private-prod ii. Subnets - Must in same VPC iii. Security Groups - Must in same VPC and attached with both Lambda. 3. Lambda Trigger: a. Archival i. EventBridge (CloudWatch Events): wis-archive-ExecuteOnceAMonth (Enabled) b. Retrieval i. S3: nab-wealthintprod-prod-wis-temp-retrieval ii. S3: nab-wealthintprod-prod-wis-archival 4. lambda Permission for both Archival and Retrieval: i. wis-archive-prod-app-S3FullAccess-LambdaRole 5. S3 lifecycle policy: a. nab-wealthintprod-prod-wis-archival - i. DeleteAfter12Years ii. MoveObjectToS3GlacierAfter3Months b. nab-wealthintprod-prod-wis-retrieval i. expires-after-a-day | 1.Manual process: Need to enter On-premises GPG password in "wis-archive-prod-ArchivalLambda" Lambda function Environment variables. passphrase => Passphrase (This applicable only on-premises files migration, for BAU it's not needed) 2. All the AWS resource and configuration for wis-archive project are ready to perform testing. |  | 0% | 1 hours? | 2021-04-30 17:00 | 2021-04-30 18:00 | Venkata Kishore K Kantipudi | Need to verify in prod http_proxy => http://forwardproxy:3128 iii. https_proxy => http://forwardproxy:3128 vi. keyArn => Lambda KMS Key ARN v. no_proxy =>localhost,127.0.0.1,169.254.169.254,s3.ap-southeast-2.amazonaws.com
7 | Auto Scheduled | y | Test Archival | 1. Make sure that some test files, which is .zip and GPG encrypted with onprem key must be present in "nab-wealthintprod-prod-wis-archival-source" S3 bucket. 2. To manually trigger the Archival lambda go to AWS Lambda screen and search for "wis-archive-prod-ArchivalLambda". Click on the function name and go into the "Test" section, type some event name and put double quotation marks ("") key value section and click on "Test" button. 3. Lambda execution will start and process the files (unzipped, decrypt, encrypt with KMS, copy into S3 "nab-wealthintprod-prod-wis-archival" and delete the files from "nab-wealthintprod-prod-wis-archival-source" S3 bucket). | Success: 1. File will archived in "nab-wealthintprod-prod-wis-archival" AWS S3 bucket with KMS encryption. 2. Delete the file form "nab-wealthintprod-prod-wis-archival-source" AWS S3 bucket. Failed: Need to check "wis-archive-prod-ArchivalLambda" lambda CloudWatch logs. |  | 0% | 30 minutes? | 2021-04-30 18:00 | 2021-04-30 18:30 | Venkata Kishore K Kantipudi
8 | Auto Scheduled | y | Test Retrieval | 1. Test for S3 Standard: Files to be retrieve, search in "nab-wealthintprod-prod-wis-archival" AWS S3 bucket. b. Select it and from "Action" menu "copy" it to "nab-wealthintprod-prod-wis-temp-retrieval" S3 bucket. c. On copy event "wis-archive-prod-RetrievalLambda" lambda will trigger, which decrypt the files and move into "nab-wealthintprod-prod-wis-retrieve" s3 bucket. d. Files will get deleted automatically from "nab-wealthintprod-prod-wis-temp-retrieval" S3 bucket as soon as Lambda "wis-archive-prod-RetrievalLambda" processed it. 2. Test for S3 Glacier: a. Search the files in "nab-wealthintprod-prod-wis-archival" S3 bucket to be retrieve. b. Select it and from "Action" menu click "Initiate Restore" , put 1 day in "Number of days that the restored copy is available" filed and select "Retrieval tier" option based on the requirement and submit "restore request". c. Restore request will get completed based on the configuration set step 2 in "Retrieval tier". d. As soon as restore request get complete "wis-archive-prod-RetrievalLambda" will get trigger and which decrypt the files and move into "nab-wealthintprod-prod-wis-retrieve" s3 bucket. | Success: 1. File will available to download in "nab-wealthintprod-prod-wis-retrieval" S3 bucket, which is in decrypted format. Operation team can download it 2. File will get permanently delete automatically after 1 day form "nab-wealthintprod-prod-wis-retrieval" S3 bucket. Failed: Need to check "wis-archive-prod-ArchivalLambda" lambda CloudWatch logs. |  | 0% | 30 minutes? | 2021-04-30 18:30 | 2021-04-30 19:00 | Venkata Kishore K Kantipudi
9 | Manual |  | Audit (Archival/Retrieval) report configuration | Go to AWS "CloudWatch" page, Click on "Log groups" from the left hand side menu. Archival: 1.In the log streams select "/aws/lambda/archive-nonprod-wis-ArchivalLambda" logs. At top click on "View Logs In Insights" page. 2. It will open "Logs Insights" page, paste the below query in "query" the text box fields @message ¦ filter @message like "Status=" ¦ parse @message "INFO: FileName=*,Timestamp=*,ObjectKey=*,Status=*" as `Source filename`,DatetimeStamp,`Archival filepath`,Status ¦ display `Source filename`,`Archival filepath`,DatetimeStamp,Status and click on save.It will ask for a name.Enter "GET_ARCHIVAL_REPORT" and leave the folder and the prefix options as default. Retrieval: 1. In the log streams select "/aws/lambda/archive-nonprod-wis-RetrievalLambda" logs. At top click on "View Logs In Insights" page. 2. It will open "Logs Insights" page, paste the below query in "query" the text box fields @message ¦ filter @message like "Status=" ¦ parse @message "INFO: FileName=*,Timestamp=*,ObjectKey=*,Status=*" as `Archival filename`,DatetimeStamp,`Retrieval filename`,Status ¦ display `Archival filename`,`Retrieval filename`,DatetimeStamp,Status and click on save.It will ask for a name.Enter "GET_RETRIEVAL_REPORT" and leave the folder and the prefix options as default. | 1. Audit report for Archival is configured 2. Audit report for Retrieval is configured. |  |  |  | 2021-04-30 19:00 | 2021-04-30 19:15 | Venkata Kishore K Kantipudi
10 | Auto Scheduled | y | Test Audit | 1. After archival lambda "wis-archive-prod-ArchivalLambda" execution get completed. 2. Go to AWS "CloudWatch" page, Click on "Insights" from the left hand side menu.It will open "Logs Insights" page. At right side click on "Queries" , It will show the list of reports. 4. To get the Archival Audit reports : Click on "GET_ARCHIVAL_REPORT" link.It will open the GET_ARCHIVAL_REPORT report page.To select the report duration click on the "Custom => Absolute" option and select the date based on the business requirement and click on "Run query". It will show the result in the table format on the same page. To download audit report click on "Export results => Download table (CSV)" it will download the CSV file on local system. 5. To get the Retrieval Audit reports : Click on "GET_RETRIEVAL_REPORT" link.It will open the GET_RETRIEVAL_REPORT report page.To select the report duration click on the "Custom => Absolute" option and select the date based on the business requirement and click on "Run query". It will show the result in the table format on the same page. To download audit report click on "Export results => Download table (CSV)" it will download the CSV file on local system. | 1. Archival Audit report is downloaded in CSV format on local system. 2. Retrieval Audit report is downloaded in CSV format on local system. |  | 0% | 30 minutes? | 2021-04-30 19:15 | 2021-04-30 19:30 | Venkata Kishore K Kantipudi
11 | Auto Scheduled |  | Decision Point & Integrated Systems Start Up - Main Go/No Go Decision |  |  |  | 0% | 30 minutes? | 2021-04-30 19:30 | 2021-04-30 20:00 | Van Lenguyen (+61 414 008 561)/ George Pavone (+61 407 272 128)

## Rollback_Plan
ID | Task Mode | Task Name | Details Task | Validation | CHG No. | % Complete | Duration | Start | Finish | Resource Names | Comments / Notes
1 | Manual | Rollback decision | [5 empty] | 2021-04-30 20:00 | 2021-04-30 20:30 | Van Lenguyen (+61 414 008 561) / George Pavone (+61 407 272 128)
2 | Auto Scheduled | Delete the "tibco-prod-app-wis-archive-CloudFormation" AWS stack. | 1. Login into AWS prod account console. 2. Go to "IAM" AWS page, click on "Roles", it will open roles details page, search for "wis-archive-prod-app-S3FullAccess-LambdaRole" role. Select it and delete it. 3. Go to "wis-archive-prod-ArchivalLambda" lambda, click on the "Configuration" then click on "VPC", click on the "Security groups" id that start with "sg-", it will open the security groups details page from the "Action" menu dropdown and click on the "Delete security groups", it will open the popup with warning saying that "Some security groups can't be deleted" and also shows the network interfaces associated it . click on the "network interfaces associated", it will open new page, select all "network interfaces associated" and from "Action" menu, click on "Delete". 4. Go to "CloudFormation" page and search for "tibco-prod-app-wis-archive-CloudFormation" stack. Select it and click on the "Delete" button. It will ask for edit termination protection click on "Edit termination protection" select Termination protection "Disabled" and click on "Save" button. 4. Select "tibco-prod-app-wis-archive-CloudFormation" stack and click on the "Delete" button. It will start deletion process. | Failed: 1. Need to check "tibco-prod-app-wis-archive-CloudFormation" stack "Events " and "Resources" section for error details . Success: 1. It will not delete the below Archive S3 bucket, AWS KMS Key and associate KMS Key Alias. i. "nab-wealthintprod-prod-wis-archival" ii." alias/nab-wealthintprod-lambda-prod-wis-archive-kmskey" iii. "alias/nab-wealthintprod-s3-prod-wis-archive-kmskey" 2. It will delete the "tibco-prod-app-wis-archive-CloudFormation" stack and below associate wis -archive project AWS resources except resources mentioned in point no.1 in success section. a. S3 buckets i. nab-wealthintprod-prod-wis-archival-source ii. nab-wealthintprod-prod-wis-archival iii. nab-wealthintprod-prod-wis-retrieval iv. nab-wealthintprod-prod-wis-temp-retrieval b. Lambda i. wis-archive-prod-ArchivalLambda ii. wis-archive-prod-RetrievalLambda c. Lambda Role i. wis-archive-prod-app-S3FullAccess-LambdaRole d. Lambda Security Group i. wis-archive-prod-app-lambda e.Lambda Permission for i. Temp Retrieval Bucket. ii. Archival Bucket f. EFS File System g. EFS mount target availability zone i. Availability zone - A ii. Availability zone - B iii. Availability zone - C h. EFS access point i. Lambda ii. S3 bucket |  |  | 1.5 hours? | 2021-04-30 20:30 | 2021-04-30 22:00 | Venkata Kishore K Kantipudi